U.S. Department of Housing and Urban Development

PUBLIC AND INDIAN HOUSING

Special Attention of:                        		Notice PIH 96-29 (HA)

Secretary's representatives;                  	Issued: May 16, 1996

Public Housing Directors;

Administrators, Area Offices               	Expires: May 31, 1997

of Native American Programs;

Public Housing Agencies; Indian              	Cross References:

Housing Authorities; Resident

Management Corporations; Resident

Councils; Resident Organizations

Subject:  Implementing Performance Standards required by the Tenant

Opportunities Program (TOP)

I.   BACKGROUND

The Tenant Opportunities Program (TOP) provides technical assistance for

various activities, including but not limited to resident management,

for resident councils/resident management corporations, as authorized by

Section 20 of the U.S. Housing Act of 1937.  The TOP provides

opportunities for resident organizations to improve living conditions

and resident satisfaction in public housing communities.

The Office of Public and Indian Housing, Office of Community Relations

and Involvement's (OCRI) strategy in developing the performance

standards was based on the fundamental principle that specific types of

training programs for residents can lead to positive outcomes.  Since

training remains an essential ingredient for the success of TOP, each

training program must result in a product or action that makes positive

change in the. resident community. Section 20(f) of the United States

Housing Act, as amended, makes resident training under TOP possible;

however, HUD must ensure that the training strategy produces the actions

and outcomes required to achieve TOP goals.  Performance Standards are

necessary to measure grantees' progress in the implementation of their

training programs.  To ensure that training activities are being

achieved, semiannual performance status reports, as well as the TOP Work

Plan will be used to evaluate the grantee's overall performance against

its task accomplishments and timeframes.

PR:     Distribution: W-3-1, R-3-1(PIH), R-6, R-7, R-9, 138-2, 138-7, RMC-2

2

II.  PURPOSE OF THIS NOTICE

Past experience has shown that training results related to any TOP

initiative have been significant and multifaceted. Training for

resident-managed activities has resulted in opportunities in economic

development, resident self-sufficiency, improved living conditions and

enhanced social services for residents.  Residents provided an

opportunity to be trained to move toward responsible roles in their

communities.  Training also enhances the functioning of the resident

council and enables it to develop skills to engage in resident-managed

activities in its community.  This Notice serves to aid grantees in

accomplishing the training tasks.

NOFAs from Fiscal Year 1988 to 1995 required that grantees develop

concrete Work Plans pursuant to the Resident Management/Tenant

Opportunities Program (RM/TOP).  The Work Plan is comprised of tasks and

timeframes to assist grantees in developing training activities during

the duration of the grant.  In the past Work Plans have not contained

specific training goals pursuant to program requirements.  Future NOFAs

will require RM/TOP grantees to develop specific training goals in their

Work Plans.  This Notice serves to assist grantees in accomplishing the

requirements.

Grantees are required to select and implement the training program(s) of

choice in accordance with the needs of the community. These programs are

not all inclusive and grantees may work with the HUD Field Offices to

establish other training programs to meet their needs provided that the

results would be measurable.

III. APPLICABILITY

This Notice applies to:

A.   Resident Councils (RCs), Resident Management Corporations (RMCs),

and Resident Organizations (ROs), with FY 1988 - FY 1995 Resident

Management/Tenant Opportunities Program Technical Assistance Grants

(RM/TOP TAG), and future TOP grantees unless otherwise indicated.

B.   HUD Field Offices of Public Housing (OPHs) and HUD Area Offices of

Native American Programs (AONAPs).

C.   Public Housing Agencies (hereinafter referred to as HAs), including

HAs funded on behalf of RCs/RMCs in FY 1988.

3

D.   This Notice does not apply to the National Resident Organizations

(NROs), Regional Resident Organizations (RROs), and Statewide

Resident Organizations (SROs) with FY 1994 - FY 1995 Tenant

Opportunity Technical Assistance Grants.  However, NROs/RROs/SROs

should be cognizant of the requirements contained in this Notice

when providing training to the RM/TOP grantees.

IV.  THE WORK PLAN AND TRAINING PROGRAMS/PERFORMANCE STANDARDS

The work plan requires that the performance standards selected as

training tasks by the RC's/RMC's/RO's must clearly demonstrate the

activities to be accomplished within 3-5 years.  Therefore, the work

Plan must be clearly written to state how training tasks will be

successfully accomplished.

Tasks I and II of the General Work Plan (see attachment) require

grantees to do the type of partnering, planning, organizing and

organizational development that will result in a successful TOP

implementation strategy.  HUD Field Offices/ONAP must ensure that the

grantees have completed all activities under these tasks prior to

advancing to remaining Tasks.

V.   TRAINING PROGRAMS/PERFORMANCE STANDARDS AND TIMEFRAMES

Training programs by which HUD will measure performance standards, will

be based on task accomplishments and timeframes; for example, how

detailed is the Work Plan, or what is the timeframe for accomplishing

the tasks, or what resources will be used to accomplish these tasks;

etc. Therefore, it is essential that training programs and timeframes be

designed to produce results.  Grantees are required to complete at least

two training programs, one of which must be the training program listed

below as number one.  These training programs are not all inclusive and

grantees may work with the HUD Field Office and the local HA to select

other training programs to meet their specific needs; however, the

results must be measurable.  Timeframes for the suggested training

programs listed below are flexible, up to the limit as established in

each activity. Failure to meet the timeframes may result in default of

the Technical Assistance Grant (TAG) Agreement. Whenever the RC/RMC/RO

hires trainers or other experts for training programs, the training must

be provided by a qualified housing management specialist, a community

organizer, the HA or other sources knowledgeable about the program.

4

Listed below are examples of detailed training programs which can be

included in the Work Plan:

1.   Train block/building/floor captains, members of the RC/RMC/RO board

and other interested residents to increase its capacity as an

organization.  Examples may include, but are not limited to,

establishing operating/planning committees and block/building/floor

captains to carry out specific organizations tasks and developing

a cohesive relationship between the residents and the local

community.

The training program must begin within 3 to 6 months after the TAG

Agreement has been executed.

All grantees must perform this training activity in a timely manner

since it serves to focus the resident community and will broaden

participation by providing specific training to a large body of

residents.

The following HUD requirements and training elements can be

included in a training program:

o    24 CFR Part 964 and Part 950 (Public/Indian Housing)

o    Procedures and guidelines governing TOP

o    Organization development

o    Conflict resolution and mediation

o    Techniques on planning and conducting organizational meetings

o    HUD regulations and policies governing the operation of low-

income housing which includes Comprehensive Grant Program

(CGP), Section 3, etc.

o    Procurement and contracting; financial management

2.   Develop strategies to decrease crime and violence by creating a

sense of community responsibility and common concerns.

This training program must be in place within six months of

completing Tasks I thru IV of the TOP work plan; however, the

results may take much longer.

5

By completing the first training activity listed in number one

above, there may be automatic progress made on this training

activity because crime and violence decreases when a sense of

community begins to develop. Community and caring, combined with

appropriate law enforcement, are the best tools against crime.

3.   Train residents to develop a tutorial and scholarship program using

a "Board of Very Important Persons (VIP)" such as Accountants,

Bankers, Lawyers, officials in public/private

agencies/organizations to provide opportunities for educational

attainment needed to perform resident-managed functions, including

institutions of higher learning.

This training program must be in place within 12 to 19 months of

completing Tasks I thru IV of the TOP Work Plan.

This training activity may not be appropriate for every resident.

The HA and grantee should work closely to develop strategies that

fit the needs of the residents living in public/Indian housing.

4.   Train residents in areas related to resident-owned businesses and

provide technical assistance for Job training, and placement in the

RMC development. This can be accomplished by using programs, such

as the Section 3 Jobs initiative or for IHA, Indian preference in

accordance with 24 CFR Part 950.175 and Section 7(b) of the Indian

Self Determination and Education Assistance Act (25 U.S.C. 450(b)).

This training program must be in place within 18 to 24 months of

completing Tasks I thru IV of the TOP Work Plan.

This training activity may be achievable if developed in

conjunction with the Section 3 technical assistance initiative and

the Comprehensive Grant Program.  The training strategy developed

to implement the first training activity listed in number one above

can facilitate a practical approach to economic development and job

training.

5.   Train and provide technical assistance to residents in resident-

managed business development and provide technical assistance.

This training program must be in place within 12 to 18 months of

completing Tasks I thru IV of the Top Work Plan.

6

This training activity would involve feasibility and market

studies, development of business plans, outreach activities and

innovative financing methods involving revolving loan funds and

legal advice in establishing a resident managed business entity.

6.   Train residents in areas related to social support needs.

This training program must be in place within 24 months of

completing Tasks I thru IV of the TOP Work Plan.

This training activity may involve feasibility studies to determine

training and social support needs, training in management-related

employment training and counseling, coordination of support

services; training for programs such as child care, early childhood

development, parent involvement, volunteer services, parenting

skills, before and after school programs; and training programs on

health, nutrition and safety.

7.   Train residents in the development of strategies to successfully

implement a youth program which will address the needs of the

youth, such as reducing crime, drug use, violence and teenage

pregnancy.

This training program must be in place 18 months of completing

Tasks I thru IV of the TOP Work Plan; however, results may take

longer.

This training activity could involve, for example, the needs and

problems of youth, improving youth initiatives that are currently

active, and training youth, housing authority staff, resident

management corporations and resident councils on youth initiatives

and program activities.

8.   Train residents in the management of public and Indian housing

developments.

This training program must be in place within 24 months of

completing Tasks I thru IV of the TOP Work Plan.

This training activity requires residents to establish a

partnership with the HA, receive training relating to property

management, and establish a dual/full management contract with the

HA.  The dual management contract allows residents to work jointly

with the HA in preparation to manage certain functions in the

development.  The full management contract allows residents to

manage certain functions at the development.  Training may involve

skills directly related to the operation, management, maintenance

and financial systems of a project, training of residents with

respect to fair housing requirements and in negotiating management

7

contracts, designing a long-range planning system and HUD

regulations and policies governing the operation of low-income

public housing.

9.   Train residents to develop a homeownership plan under 5(h) or an

equivalent program.

This training program must be in place within 18 months of

completing Tasks I thru IV of the TOP Work Plan.

Training would involve determining feasibility for homeownership by

residents including assessing the feasibility of other housing

(including HUD-owned or HUD-held single or multifamily) affordable

for purchase by residents.

This training activity may result in residents developing a

homeownership plan under 5(h) or an equivalent program and submit

the plan to HUD for approval.

VI.  DIRECTION

The Field Offices (FOs), Area Offices of Native American Program

(AONAPs) and grantees are required to evaluate TOP work plans to ensure

that they meet the training activities of this Notice.  The following

actions are required:

1.   The HUD FO/AONAPs Community Relations and Involvement Specialists

(CRIS) and TOP grantees in partnership with their HAs should assess

work plans to determine if goals are result-oriented and contain

performance standards and realistic timeframes within the

prescribed timeframes specified above that reflect outcome,

products or deliverables.

2.   If the grantees' current work plans lack an acceptable strategy

towards specific outcomes and goals, the FO/AONAP must notify

grantees that their work plans must be revised to meet the

requirements established in this Notice.

8

3.   Grantees must provide the revised work plans to the local FO/AONAP

for review and approval within 60 days from the date of this

Notice.

4.   No action is necessary if the grantees' work plans meet the

objectives contained in this Notice.

Deputy Assistant Secretary for

Distressed and Troubled

Housing Recovery