Steps for Lead Hazard Control Project

from Unit Enrollment to Clearance

and Update on their Relation to the

HUD Guidelines for Evaluation and Control of Lead-Based Paint Hazards in Housing, Second Edition

September 4, 2012

| Project step | HUD Guidelines references | HUD Guidelines – Key Points |
| --- | --- | --- |
| - Before beginning | - Chapter 2, Where to Go for Help | - Investigate availability of funding (match, leveraging) sources, evaluation contractors / staff, and hazard control contractors |
|  | - Chapter 1, Introduction - Chapter 3, Planning to Control Lead Hazards - Appendix 6, Lead Paint Rules | - Review applicability of federal, state, tribal and local regulations and guidance |
| - If federal funds involved or when otherwise required: approval of environmental review and release of funds | - Chapter 18, Historic Preservation | - Ensure that lead issues are integrated into environmental review and supporting documentation for request for release of funds |
| - Unit intake and enrollment |  |  |
| - Property eligibility determination completed |  |  |
| - Tier II environmental review, including State Historical Preservation Officer | - Chapter 18 | - Ensure that lead issues are integrated into environmental review at the project level |
| - Eligibility determination completed, if applicable |  |  |
| - Verification of blood lead testing | - Chapter 1 - Chapter 2, section III, health - Chapter 16, investigation and treatment of houses with EBL children | - Updated CDC EBL guidance - Lead regulatory framework - Updated health contacts |
| - Lead-paint inspections and/or risk assessments, as required, completed | - Chapter 5, Risk Assessment, section VI, final report - Chapter 7, LBP Inspection, sections IV.I.3 (single-family report) and VI.E (multifamily report) - Appendix 8.1, example of risk assessment report - Appendix 9, lead-based paint liability insurance | - Ensure that the inspection / risk assessment firm has adequate insurance that covers its lead evaluation activities - Inspection / risk assessment reports must comply with EPA / State / Tribal requirements - Risk assessment must identify ALL hazards on ENTIRE property (e.g., not just windows) - EPA-recognized chemical test kits are NOT allowed to make positive determination of presence of LBP (as of 9/4/2012) - Ceramic tile / bath fixtures are not painted; some risk assessors test them as potential sources of lead hazard during work - Composite sampling is discouraged - Inspection / risk assessment report must provide an interpretation (LBP? LBP hazards? if yes, where?), not just the data - To the extent provided in grants / contracts, project documentation, such as inspection and risk assessments reports, may be examined by funding organization / agency - Grantees should NOT pay for inadequate or shoddy inspections or risk assessment reports |
| - Laboratory analysis of samples | - Chapter 5, section IV, laboratory procedures - Chapter 7, sections I.B.1, where to find labs, and I.G and I.H, for qualifications - Chapter 15, Clearance, section IV.A.1, wipe sampling | - Laboratory analyzing paint chips, dust or soil for lead must be EPA-recognized under NLLAP for that analysis - On-site dust analysis for risk assessment or clearance must be done by NLLAP-recognized laboratory |
| - Inspection / risk assessment results communicated with property owner | - Chapter 2, sections II.A, owners; and IV.A, lead evaluators | - Risk assessors and property owners planning lead hazard control work should find that close communication facilitates progress |
| - Work specifications developed | - Risk assessment report: see Chapter 5, section VI.A - Chapter 9, worker protection - Appendix 7.3 Generic LBP contract specifications - Appendix 7.4, soil hazard control spec guidance | - Make sure all hazards identified by the risk assessment are addressed in the work write-up / scope of work - Specifications must include compliance with applicable HUD, EPA and OSHA standards (or State / Tribal / local standards, if more protective) - Specifications for disturbing ceramic tile or fixtures containing lead must require OSHA compliance |
| - Bid process, Contractor selection completion, Verification of contractor’s firm and worker licenses and certification | - Chapter 2, section II.A, owners - Appendix 6, regulations - Appendix 9, LPB liability insurance | - Require adequate insurance that covers lead hazard control activities in the work write-up / project specifications - Window replacement intended as control of lead hazards is abatement; abatement firms and workers are required - Interim controls activities for rehab or renovation requires RRP firms and supervisors certified, and for HUD-funded work, all workers certified (not just trained) |
| - Occupant protection plan, and Temporary relocation plan completed and discussed with owner and occupants | - Chapter 8 for occupant protection; in particular, sections II, general, and IV, temporary relocation | - Occupant protection and temporary relocation should be integrated the entire planning process |
| - Interim controls and / or hazard abatement completed; other work on property completed | - Chapter 8 for worksite prep., Table 8.1, and section III - Chapter 10,Waste - Chapter 11, Interim Controls - Chapter 12, Abatement - Chapter 13, Encap-sulation Abatement - Chapter 14, Cleanup | - Use low-dust methods - High-dust jobs are likely for jobs over 6 sq. ft. of paint disturbance that don’t have proper precautions - Do not use EPA’s prohibited work practices; do not use HUD’s prohibited work practices HUD’s if work is HUD-funded, or to ensure additional caution - Handle waste properly in accordance with EPA RCRA and State / Tribal / local laws and regulations |
| - Quality control – Contractor performance monitored | - Chapters 8, and 10 to 15 | - Integrate planning & implementing contractor performance and quality control monitoring through project - To the extent provided in grants / contracts, project documentation, such as LBP inspection reports, risk assessment reports, on-site monitoring reports, may be examined by funding organization / agency |
| - Clearance evaluations completed and reported; re-occupancy allowed | - Chapter 15 - Clearance must be performed on entire unit - Follow Table 15.1, number and location of samples - Consider using Form 15.4, Clearance Report Review Worksheet, to document clearance for project file | - Clearance examination required for all abatement projects and for HUD-assisted interim control projects above de minimis amounts - To the extent provided in grants / contracts, project documentation, such as clearance examination reports, may be examined by funding organization / agency - Clearance examination must be done by a clearance examiner – an inspector or risk assessor (possibly assisted by a sampling technician) - If work is HUD-funded, clearance examiner must be independent of the hazard control contractor; HUD recommends this for other work as well - Clearance for exterior work is only a visual assessment - Use only proper individually-packaged dust wipes - Clearance report must include an interpretation (pass / fail; and if fail, identify affected areas to re-clean and retest), and not just the data - Review clearance results to ensure correct interpretation - Permit re-occupancy only after clearance results received and passed |
| - Ongoing maintenance plan developed and communicated with property owner / occupants | - Chapter 6, Ongoing Lead-Safe Maintenance | - Grantee tells how units will be monitored and evaluated to ensure they remain lead-safe - Owner establishes and manages lead-safe maintenance program, including hazard evaluation and control, resident education and communication, and documentation |
| - Notification and disclosure | - Chapter 5, section VI, final report - Chapter 7, sections IV.I.3 and VI.E, reports - Chapter 15, section X, report preparation | - Provide owner with all LBP testing results, summaries of hazard control treatments, and clearance results - Provide notice of owner’s duty to disclose the results to tenants and buyers |
| - Final invoices (and supporting documentation) for the project submitted by contractors; invoice (and supporting documentation) submitted to funding organization / agency |  | - Double-check documentation to ensure that all work was done in accordance with the Guidelines and all applicable regulations and policies as part of allowing authorization of payment by funding organization / agency |